## Sheet1
Timing: | Activity: | Responsible Party / Assigned To:
1. Planning Stage | Decide on Date, Time, & Purpose
1. Planning Stage | Determine Where event to be held
1. Planning Stage | Who will be the Race Director?
1. Planning Stage | Determine Cost/Entry Fee
1. Planning Stage | Design and produce Entry Form
1. Planning Stage | Who will be responsible for water stop?
1. Planning Stage | Who will be responsible for registration?
1. Planning Stage | Get information on Website
2. Pre-Race | Secure Permits if needed (parade permits - Police Dept. City of Hburg)
2. Pre-Race | Confirm venue is secured for event - may need a deposit, etc.
2. Pre-Race | Secure Sponsors
2. Pre-Race | Design T-Shirts
2. Pre-Race | Design Awards/Trophies
2. Pre-Race | Secure volunteers for course monitors
2. Pre-Race | Secure volunteers for registration
2. Pre-Race | Secure police/sheriff escort
2. Pre-Race | Secure Ambulance service if possible
2. Pre-Race | Determine Date of Goody Bag Preparations
2. Pre-Race | Who will announce results?
2. Pre-Race | Who will announce door prizes?
2. Pre-Race | Order T-Shirts - for Participants
2. Pre-Race | Order T-Shirts - for Volunteers
2. Pre-Race | Order Awards/Trophies
2. Pre-Race | Secure Door Prizes
2. Pre-Race | Get out promotional material on race
2. Pre-Race | Bibs - may need different colors
2. Pre-Race | Ribbons for 1 Mile Participants
2. Pre-Race | Order/Confirm post-race beverages & amounts
2. Pre-Race | Gather boxes to hold Goody Bags
2. Pre-Race | Prepare "Goody Bags" for Pre-Registered Entrants
2. Pre-Race | Make sure Mile Marker signs are in good order
2. Pre-Race | May need to order paper for results printer
2. Pre-Race | May need to order safety pins
2. Pre-Race | Ensure you have or order "flags" for finish shoot
2. Pre-Race | Assign five people to work finish line (2 for labels; 2 for printer/timer & 1 supervisor)
2. Pre-Race | Organize trailer
3. Week of Race | Secure post-race beverages
3. Week of Race | Secure post-race snacks/food
3. Week of Race | Mark the course
3. Week of Race | Have copies of Course Maps for day of race
3. Week of Race | Have Membership Enrollment forms
3. Week of Race | Determine who will say prayer
3. Week of Race | Public Address System
3. Week of Race | Batteries for Results Printer
3. Week of Race | Batteries for PA System
3. Week of Race | Toilet Paper - Other Plumbing needs (plunger, etc)
3. Week of Race | Pens
3. Week of Race | Safety pins
3. Week of Race | Extension Cords
3. Week of Race | Music
3. Week of Race | Race Clock
3. Week of Race | Extra Entry Forms for Day of Race
3. Week of Race | Finish Labels
3. Week of Race | Finish Board
3. Week of Race | Results Board (may need more than 1)
3. Week of Race | Who is responsible for compiling results?
3. Week of Race | Cups
3. Week of Race | Ice
3. Week of Race | Tables
3. Week of Race | Have some cash on hand for registration
3. Week of Race | Need money box or money bags
3. Week of Race | May need garbage cans & Liners
3. Week of Race | Secure enough pens/pencils
4. Race Day | Set Up clock
4. Race Day | Set Up finish shoot
4. Race Day | Set Up Water Stop
4. Race Day | Set Up Registration - separating pre-registered from need to register seems to work best
4. Race Day | Set Up Refreshments Tables
4. Race Day | Check restroom facilities
4. Race Day | Announce/thank sponsors
4. Race Day | Announce Door Prizes
4. Race Day | Announce Awards
4. Race Day | Clean up venue
4. Race Day | Pick up mile marker signs from course
4. Race Day | Prepare summary of event - Funds raised, # of participants, etc.
4. Race Day | Get race results to website & paper
4. Race Day | Organize trailer for next race
Also see: http://www.coolrunning.com/engine/5/5_1/265.shtml